## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Bob Smith | 555-5676 | 8 | Mon - Fri
Sue Jones | 555-2567 | 8 | Mon - Fri
Tim Thomas | 555-2243 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | You
Documentation Developer | You
Data Warehouse Developer | You
ETL developer | You
Cube Developer | You
Report Developer | You
Testers | You
Release Manager | You

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 3 | ***
Planning and Documenting: | 3 |  | ***
Create the Data Warehouse | 3 |  |  | ***
Extract, Transform, and Load: | 6 |  |  |  | *** | ***
Create Cubes: | 6 | [5 empty] | *** | ***
Create Reports: | 3 | [7 empty] | ***
Test the Solution: | 3 | [8 empty] | ***
Approve, Release, and Prepare for next version: | 3 | [9 empty] | ***

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 1
Talk to Mangers
Talk to Users
Talk to DBA
| Document Requirements | Create an informal overview | 1
Create a BI solution worksheet
| Locate Data | Review database tables | 1
Review invoice documents
Review sales awards program
| Discuss Feasibility | Decide if the solution will work
3
Planning and Documenting: | Define Team Roles | What role fit this solution?
| Define Team Members | Who will fill each role?
| Define Team Schedule | When will we need them?
| Discuss Feasibility | Decide if the solution will work
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS
Verify a time slot of Solution automation jobs
| Define Security requirements | Decide which groups will have access to what?
| Define Licensing requirements | Verify that the company has sufficient licensing
| Estimate the cost | Hours * Wages + and additional 10% for unknowns
| Discuss Feasibility | Decide if the solution will work
| Create formal documents | Complete BI solution worksheet | 1
|  | Create a Development Document | 2
3
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
3
Test the Solution: | Requirements | Verify naming | 2
Verify data domains
Verify formula results
Verify presentation formatting
| Performance | Test SSIS ETL performance | 1
Test SSAS Processing performance
Test SSRS Report performance
3
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
Create a formal overview document
Create a lessons learned document
3
|  | TOTAL | 33

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type | Transformations and ETL functions | Example Data
DWNorthwindLite | Data Warehouse | NorthwindLite | Database | Database |  | NA
DWNorthwindLite.dbo.FactOrders | Fact Table | NorthwindLite.dbo.Orders | Table | Table | NA | NA
DWNorthwindLite.dbo.FactOrders.OrderID | Dimension Key Column | NorthwindLite.dbo.Orders.OrderID | int | int | [OrderId] = Orders.OrderID | 1
NA | NA | NorthwindLite.dbo.Orders.CustomerID | nchar(5) | NA | Replaced by surrogate key | NA
DWNorthwindLite.dbo.FactOrders.CustomerKey | Dimension Key Column | NA | NA | int | [CustomerKey] = Lookup in DimCustomers table | 1
NA | NA | NorthwindLite.dbo.Orders.OrderDate | datetime | NA | Replaced by surrogate key | NA
DWNorthwindLite.dbo.FactOrders.OrderDateKey | Dimension Key Column | NA | NA | int | [OrderDateKey] = Lookup in DimDates table | 20141231
DWNorthwindLite.dbo.FactOrders | Fact Table | NorthwindLite.dbo.OrderDetails | Table | Table | NA | NA
DWNorthwindLite.dbo.FactOrders.OrderID (Merged) | Dimension Key Column | NorthwindLite.dbo.OrderDetails.OrderID | int | int | Redundent. Using parent id column in Orders | 1
NA | NA | NorthwindLite.dbo.OrderDetails.ProductID | int | NA | Replaced by surrogate key | NA
DWNorthwindLite.dbo.FactOrders.ProductKey | Dimension Key Column | NA | NA | int | [ProductKey] = Lookup in DimProducts table | 1
DWNorthwindLite.dbo.FactOrders.ActualOrderUnitPrice | Measure Column | NorthwindLite.dbo.OrderDetails.UnitPrice | money | money | [ActualOrderUnitPrice] = OrderDetails.UnitPrice | 9.99
DWNorthwindLite.dbo.FactOrders.ActualOrderQuantity | Measure Column | NorthwindLite.dbo.OrderDetails.Quantity | smallint | int | [ActualOrderQuantity] = OrderDetails.Quantity | 10
DWNorthwindLite.dbo.DimProducts | Dimension Table | NorthwindLite.dbo.Categories | Table | Table | NA | NA
DWNorthwindLite.dbo.DimProducts.ProductCategoryID | Dimension Column | NorthwindLite.dbo.Categories.CategoryID | int | int | [ProductCategoryID] = Products.CategoryID | 1
DWNorthwindLite.dbo.DimProducts.ProductCategoryName | Dimension Column | NorthwindLite.dbo.Categories.CategoryName | nvarchar(15) | nVarchar(100) | [ProductCategoryName] = CAST(Categories.CategoryName as nVarchar(100)) | Cat1
DWNorthwindLite.dbo.DimProducts | Dimension Table | NorthwindLite.dbo.Products | Table | Table | NA | NA
DWNorthwindLite.dbo.DimProducts.ProductKey | Dimension Key Column | Generated | na | int | Auto Generated with Identity | 1
DWNorthwindLite.dbo.DimProducts.ProductID | Dimension Column | NorthwindLite.dbo.Products.ProductID | int | int | [ProductID] = Products.ProductID | 1
DWNorthwindLite.dbo.DimProducts.ProductName | Dimension Column | NorthwindLite.dbo.Products.ProductName | nvarchar(40) | nVarchar(100) | [ProductName] = CAST(Products.ProductName as nVarchar(100)) | Prod1
DWNorthwindLite.dbo.DimProducts.ProductCategoryID (merged) | Dimension Column | NorthwindLite.dbo.Products.CategoryID | int | int | NA | 1
DWNorthwindLite.dbo.DimProducts.StartDate | SCD Column | NA | NA | int | [StartDate] = -1 [Unknown] | -1
DWNorthwindLite.dbo.DimProducts.EndDate | SCD Column | NA | NA | int | [EndDate] = Null | 20141231
DWNorthwindLite.dbo.DimProducts.IsCurrent | SCD Column | NA | NA | char(3) | [IsCurrent] = 'Yes' | Yes
DWNorthwindLite.dbo.DimCustomers | Dimension Table | NorthwindLite.dbo.Customers | Table | Table | NA | NA
DWNorthwindLite.dbo.DimCustomers.CustomerKey | Dimension Key Column | Generated | na | int | Auto Generated with Identity | 1
DWNorthwindLite.dbo.DimCustomers.CustomerID | Dimension Column | NorthwindLite.dbo.Customers.CustomerID | nchar(5) | nchar(5) | [CustomerID] = Customers.CustomerID | ALFKI
DWNorthwindLite.dbo.DimCustomers.CustomerName | Dimension Column | NorthwindLite.dbo.Customers.CompanyName | nvarchar(40) | nVarchar(100) | [CustomerName] = CAST(Customers.CompanyName as nVarchar(100)) | Alfreds Futterkiste
NA | Dimension Column | NorthwindLite.dbo.Customers.ContactName | nvarchar(30) | NA | NA | NA
NA | Dimension Column | NorthwindLite.dbo.Customers.Address | nvarchar(60) | NA | NA | NA
DWNorthwindLite.dbo.DimCustomers.CustomerCity | Dimension Column | NorthwindLite.dbo.Customers.City | nvarchar(15) | nVarchar(100) | [CustomerCity] = CAST(Customers.City as nVarchar(100)) | Berlin
DWNorthwindLite.dbo.DimCustomers.CustomerCountry | Dimension Column | NorthwindLite.dbo.Customers.Country | nvarchar(15) | nVarchar(100) | [CustomerCountry] = CAST(Customers.Country as nVarchar(100)) | Germany
DWNorthwindLite.dbo.DimCustomers.StartDate | SCD Column | NA | NA | int | [StartDate] = -1 [Unknown] | -1
DWNorthwindLite.dbo.DimCustomers.EndDate | SCD Column | NA | NA | int | [EndDate] = Null | 20141231
DWNorthwindLite.dbo.DimCustomers.IsCurrent | SCD Column | NA | NA | char(3) | [IsCurrent] = 'Yes' | Yes
DWNorthwindLite.dbo.DimDates | Dimension Table | NA | NA |  | NA | NA
DWNorthwindLite.dbo.DimDates.DateKey | Dimension Key Column | NA | NA | int | Cast(Convert(nVarchar(50), @DateInProcess, 112) as int) | 20141231
DWNorthwindLite.dbo.DimDates.USADateName | Dimension Column | NA | NA | nVarchar(100) | DateName(weekday, @DateInProcess) + ', ' + Convert(nVarchar(100), @DateInProcess, 110) | Monday, 12/31/2014
DWNorthwindLite.dbo.DimDates.MonthKey | Dimension Column | NA | NA | int | Cast(Left(Convert(nVarchar(50), @DateInProcess, 112), 6) as int) | 201412
DWNorthwindLite.dbo.DimDates.MonthName | Dimension Column | NA | NA | nVarchar(100) | DateName(month, @DateInProcess) + ' - ' + DateName(YYYY,@DateInProcess) | December, 2014
DWNorthwindLite.dbo.DimDates.QuarterKey | Dimension Column | NA | NA | int | Cast(DateName(YYYY,@DateInProcess) + '0' + (DateName(quarter, @DateInProcess) ) as int) | 201401
DWNorthwindLite.dbo.DimDates.QuarterName | Dimension Column | NA | NA | nVarchar(100) | 'Q' + DateName(quarter, @DateInProcess) + ' - ' + Cast( Year(@DateInProcess) as nVarchar(50) ) | Quarter 1, 2014
DWNorthwindLite.dbo.DimDates.YearKey | Dimension Column | NA | NA | int | Year(@DateInProcess) | 2014
DWNorthwindLite.dbo.DimDates.YearName | Dimension Column | NA | NA | nVarchar(100) | Cast(Year(@DateInProcess ) as nVarchar(50)) | 2014
Object Name | Description | Source | Source Type | Destination Type | Transformations and ETL functions | Example Data

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description